## How to use this Evaluation Framework
1. Add the name of your project at the top of the template.
2. Fill in the sentences from your Theory of Change under the headings numbered 1, 2, 3 and 4.
3. Complete the rest of the table using the guidance below.
Terms such as inputs and activities, or outputs and outcomes, or outcomes and impact, are often used interchangeably within logic models and theories of change, which can make it difficult to decide which to use and in what order.
We have opted for the definitions below. However, we encourage a flexible approach where necessary – for example, leaving the outcomes column blank if these immediate changes are less relevant than the short- to medium-term impact for your project.

Row A: Details of inputs, activities, outputs, outcomes etc.
- Inputs
  What do you need to (or can you) put into the project? This can include project staff, funding, data and expertise
- Activities
  What do you do with your inputs to produce project outputs? For example, plan a workshop.
- Outputs
  Outputs are the elements of your project that can be evaluated to see how well the delivery process went. Outputs are easily measurable as they are direct results of the inputs and activities, such as workshops delivered.
- Outcomes
  What are the immediate changes that occur for beneficiaries as a result of the outputs,. i.e., perceived changes in attitudes, or confidence and skills when assessing content to judge whether information is genuine or not.
- Short-medium term impact
  What are the overall intended results of your project for participants; for example, changes in their behaviour, such as increased use of sources of reliable information because of their change in attitude, confidence or skills.
If you do not have the resources to do this step yourself, it can be good practice to look for evaluations of similar interventions which have already demonstrated that achieving similar outcomes leads to the desired short /medium-term impacts. While this is not as compelling as producing your own data, it is better than not providing any evidence for why you think your outcomes will lead to a particular impact.
Long-term impact
What are the changes in overall societal habits that could be linked to the changes in attitudes and behaviour of your participants? i.e. a better-informed public more resilient to mis- and disinformation. For smaller projects, demonstrating long-term impact won’t be desirable, given the numbers of participants involved. But it is important to think about how your project’s goals could contribute, alongside projects by other organisations, to a wider societal issue.
Row B: Who are the relevant target groups?
This will depend on the format of your project, and how it will be delivered. It will usually be the people to whom you deliver your initiative. But, for example when considering writing your workshop content, the target group would be different (for example, educators). Capturing which target groups are involved helps you know whom to approach in order to evaluate which factors influenced whether the intervention was successful.
Row C: What relevant data do you need?
Evaluations are only as good as the quality of the information that informs them, so data gathering throughout the project is vital. The type of data may differ across the process; we’ve made some suggestions below.
As noted above, if there is data that you would like to collect but this is not feasible, consider whether you can get evidence from other evaluations that support your assumptions.
Row D: What methods will you use to collect the data?
Here, fill in the data methods you plan to use for each stage. For more information and tips on the range of methods you could think about, please see our Doing section.
Row E: What factors beyond your control might influence this stage?
Here it is good practice to note external factors that might disrupt your planning, and your evaluation process, but that were beyond your control. This will help for future iterations of your initiative.

## Evaluation Framework
Name of project: ____________________________________________

1 Define the ‘problem’	2 What are you doing about the problem and with whom?	3 What differences will your intervention make?	4 How could these differences contribute to wider societal change?
Insert your Theory of Change sentences here	Insert your Theory of Change sentences here	Insert your Theory of Change sentences here	Insert your Theory of Change sentences here

	Inputs	Activities	Outputs	Outcomes	Short/medium- term impact	Long-term impact
A Details of inputs, activities, outputs, outcomes etc.
B Who are the relevant target groups?
C What relevant data do you need?
D What methods will you use to collect the data?
E What factors beyond your control might influence this stage?